## Dashboard
Courses + Pets RN Migration — Dashboard
Metric | Value | Target / Meaning | Notes
Total WBS tasks |  | 11 work packages | Tasks 1.0 through 11.0
Tasks done |  | 11 | Set Done with dropdown
Tasks remaining |  | 0 at M9 | Calculated
Overall completion |  | 100% | Task-count based
Requirements |  | 36 | Courses, pets, platform, and gates
Critical requirements |  | All verified | No open critical requirement at M9
Milestones signed off |  | 10 | M0-M9
Open/active risks |  | 0 | Escalate Critical/High
Sprint start |  | 2026-07-25 | Day 1
Target completion |  | 2026-08-20 | Day 20
Working days remaining |  | 0 at target | Schedule starts on Saturday, then weekdays
Scope guardrail | iOS only | NO Unity/AR core | Android and Unity/AR work excluded
Current phase gate | M3 → M7 → M8 | Sign-off required | Screens wait for M3; polish waits for M7; release waits for M8

## Project Info
Project Metadata | Value
Project Name | Courses + Pets React Native Migration
Project ID | RN-CP-2026-001
Start Date | 2026-07-25
Target Completion | 2026-08-20
Total Working Days | 20
Target Platform | iOS only
Source | frontend-web courses, lessons, pets, auth, i18n, and gamification
Target | mobile/rn (Expo SDK 57 / React Native)
Core Scope | Courses + course detail + non-AR lesson player + pets + gamification + navigation
Explicit Exclusion | NO Unity/AR core changes; NO Android-specific work; dormant AR files remain untouched
Required Gates | M3 foundation approval → M7 integration review → M8 iOS smoke sign-off → M9 release ready
API Configuration | EXPO_PUBLIC_API_URL only; bearer authentication; no hardcoded production URL
Status | Active
Owner | Edu-platform mobile team
Schedule Convention | Day 1 is 2026-07-25; remaining working days are Monday-Friday

## Milestones
Milestone_ID | Milestone_Name | Target_Date | Done | %_Complete | Status | Dependencies | Risk_Level | Sign_Off | Gate / Acceptance Notes
M0 | Scope & Baseline Locked | 2026-07-25 | TRUE | 10000% | Completed | None | Green | FALSE | TRUE | Scope confirms courses + pets only; Unity/AR core and Android excluded. U-1..U-10 captured 2026-07-26 (see docs/migration/m0-user-inputs.md). U-1: https://edu-platform-api-do20.onrender.com. U-7: Mac Day Aug 9.
M1 | Auth & App State Ready | 2026-07-27 | FALSE | 0% | Not Started | M0 | Amber | FALSE | Gate: authenticated app shell restores and clears sessions safely.
M2 | Design System & i18n Ready | 2026-07-29 | FALSE | 0% | Not Started | M1 | Green | FALSE | Gate: reusable clay tokens and en/vi catalogs approved.
M3 | Foundation Phase Gate | 2026-07-31 | FALSE | 0% | Not Started | M1,M2 | Amber | FALSE | Mandatory sign-off on API contracts, types, services, hooks, and backend audit before screens.
M4 | Course Catalog Ready | 2026-08-05 | FALSE | 0% | Not Started | M3 | Green | FALSE | Course list acceptance criteria pass.
M5 | Course Learning Flow Ready | 2026-08-11 | FALSE | 0% | Not Started | M4 | Amber | FALSE | Course detail and non-AR lesson player pass; AR references degrade safely.
M6 | Pet Hub Ready | 2026-08-12 | FALSE | 0% | Not Started | M3 | Amber | FALSE | Pet catalog, active selection, care actions, and unlock UI pass.
M7 | Feature Integration Gate | 2026-08-17 | FALSE | 0% | Not Started | M5,M6 | Amber | FALSE | Mandatory reviewer sign-off for gamification, tabs, localization, and scope compliance.
M8 | iOS Smoke Gate | 2026-08-19 | FALSE | 0% | Not Started | M7 | Amber | FALSE | iOS-only configuration and manual smoke checklist pass in an available iOS environment.
M9 | Migration Release Ready | 2026-08-20 | FALSE | 0% | Not Started | M8 | Green | FALSE | Final acceptance, documentation, and handoff complete; Unity/AR core remains untouched.

## Requirements
Req_ID | Category | Requirement_Description | Priority | MoSCoW | Status | Done | Verification_Method | WBS_Link | Evidence / Notes
REQ-001 | Authentication | The RN app shall restore a valid authenticated session at launch. | Critical | Must | Not Started | FALSE | Launch with a stored valid token | 1.0
REQ-002 | Authentication | Authentication tokens shall be stored only with expo-secure-store and removed on logout. | Critical | Must | Not Started | FALSE | Login, inspect behavior, then logout and relaunch | 1.0
REQ-003 | Authentication | Expired or rejected sessions shall return the user to AuthScreen without a crash loop. | Critical | Must | Not Started | FALSE | Use an invalid or expired token | 1.0
REQ-004 | Courses | The app shall list available courses with localized title, level, topic, and progress states. | Critical | Must | Not Started | FALSE | Authenticated API and UI test | 5.0
REQ-005 | Courses | The course catalog shall provide loading, empty, error, and retry states. | High | Must | Not Started | FALSE | Simulate slow, empty, and failed responses | 5.0
REQ-006 | Courses | Selecting a course shall open its details and ordered lesson list. | Critical | Must | Not Started | FALSE | Navigate from catalog to course details | 6.0
REQ-007 | Courses | Course details shall show completion progress and lesson availability. | High | Should | Not Started | FALSE | Compare UI with API response | 6.0
REQ-008 | Lessons | The lesson player shall support non-AR flashcard and/or quiz lesson content. | Critical | Must | Not Started | FALSE | Complete representative lesson content | 7.0
REQ-009 | Lessons | Completing a lesson shall call the authenticated completion endpoint and refresh progress. | Critical | Must | Not Started | FALSE | Complete a lesson and verify refreshed progress | 7.0
REQ-010 | Lessons | A lesson containing an AR reference shall show a localized unavailable placeholder and shall not invoke Unity or AR code. | Critical | Must | Not Started | FALSE | Open a lesson fixture containing an AR reference | 7.0
REQ-011 | Pets | The pet hub shall list available, locked, active, and evolving pet states. | Critical | Must | Not Started | FALSE | Compare pet grid against API fixture | 8.0
REQ-012 | Pets | Users shall be able to select an eligible pet as active. | Critical | Must | Not Started | FALSE | Select an unlocked pet and refresh | 8.0
REQ-013 | Pets | Supported feed, play, and care actions shall update pet state and handle API errors. | High | Should | Not Started | FALSE | Run each supported pet action | 8.0
REQ-014 | Pets | Pet unlock and evolution feedback shall use RN-native cards and modals without 3D or AR viewers. | High | Should | Not Started | FALSE | Trigger unlock/evolution fixture | 8.0
REQ-015 | Gamification | The app shall show current XP and level using the existing clay progress component. | High | Must | Not Started | FALSE | Compare XP display against summary endpoint | 9.0
REQ-016 | Gamification | The app shall show the current streak with a localized state. | High | Should | Not Started | FALSE | Compare streak display against API | 9.0
REQ-017 | Gamification | Pet unlock conditions shall use backend-provided progress and eligibility data. | Critical | Must | Not Started | FALSE | Verify locked and eligible fixtures | 9.0
REQ-018 | Navigation | Authenticated navigation shall expose Home, Courses, Pets, and a Profile placeholder as bottom tabs. | Critical | Must | Not Started | FALSE | Navigate all tabs and back paths | 10.0
REQ-019 | Navigation | Existing non-migration routes shall remain available and shall not be deleted. | High | Must | Not Started | FALSE | Review route configuration and smoke paths | 10.0
REQ-020 | Localization | Every new user-visible string shall be sourced from the English and Vietnamese catalogs. | Critical | Must | Not Started | FALSE | Search new UI files and switch locale | 3.0
REQ-021 | Localization | Changing locale shall update visible migration screens without restarting the app. | High | Should | Not Started | FALSE | Toggle en/vi on each new screen | 3.0
REQ-022 | Design | New screens shall reuse ClayCard, ClayButton, ClayProgressBar, and shared design tokens. | High | Must | Not Started | FALSE | Component and visual review | 2.0
REQ-023 | Design | Course and pet themes shall meet readable contrast, touch target, and dynamic text expectations. | High | Should | Not Started | FALSE | Accessibility review on iOS | 2.0
REQ-024 | API | The API base URL shall come from EXPO_PUBLIC_API_URL and shall not be hardcoded. | Critical | Must | Not Started | FALSE | Static review and environment smoke test | 4.0
REQ-025 | API | Authenticated course, pet, and gamification requests shall send the bearer token. | Critical | Must | Not Started | FALSE | Inspect requests in a test environment | 4.0
REQ-026 | API | Mobile services shall match backend route and response contracts rather than legacy web assumptions. | Critical | Must | Not Started | FALSE | Contract audit and typed fixture tests | 4.0
REQ-027 | API | Client mutations shall not trust or submit a user identity where the backend derives it from the token. | Critical | Must | Not Started | FALSE | Request payload review | 4.0
REQ-028 | Reliability | Migration screens shall handle offline and server-error states without crashing. | High | Must | Not Started | FALSE | Disable network and retry | 5.0
REQ-029 | Quality | TypeScript shall compile without migration-introduced errors. | Critical | Must | Not Started | FALSE | Run npx tsc --noEmit | 11.0
REQ-030 | Quality | The migrated flow shall remain stable during a 10-minute iOS smoke session. | Critical | Must | Not Started | FALSE | Manual iOS smoke checklist | 11.0
REQ-031 | Platform | This sprint shall target iOS only; Android-specific implementation and validation are excluded. | Critical | Must | Not Started | FALSE | Scope and diff review | 11.0
REQ-032 | Scope | Unity and AR core files shall not be modified, renamed, deleted, or newly coupled to migration screens. | Critical | Must | Not Started | FALSE | Git diff scope audit | 11.0
REQ-033 | Scope | Existing dormant AR files in mobile/rn shall remain in place and untouched. | Critical | Must | Not Started | FALSE | Git diff scope audit | 11.0
REQ-034 | Phase Gate | UI screen implementation shall not begin until M3 foundation sign-off is recorded. | Critical | Must | Not Started | FALSE | M3 Sign_Off is TRUE before WBS 5.0-8.0 starts | 4.0
REQ-035 | Phase Gate | Final polish shall not begin until M7 integration sign-off is recorded. | Critical | Must | Not Started | FALSE | M7 Sign_Off is TRUE before WBS 11.0 starts | 10.0
REQ-036 | Phase Gate | Release readiness shall require M8 iOS smoke sign-off. | Critical | Must | Not Started | FALSE | M8 Sign_Off is TRUE before M9 | 11.0
REQ-CLAY-001 | Design | All new UI screens MUST use existing claymorphic components (ClayCard, ClayButton, ClayProgressBar, ProgressTracker) and the tokens from mobile/rn/src/design/tokens.ts. No new visual styles — no flat/glassmorphism/material defaults, no raw hex colors, no raw inline shadows, no new font families, no new shadow presets. | Critical | Must | Not Started | FALSE | Reviewer §12 of the RN migration plan; rg -n "'#[0-9a-fA-F]{3,6}'" mobile/rn/src returns only allowed files | 2.0 | WBS 2.0 token extension merged; Rule-0 grep passes on every PR

## WBS Checklist
WBS_ID | Task_Name | Description | Phase | Priority | Effort_Hours | Start_Date | End_Date | Done | Status | Predecessors | Milestone | Blockers / Notes
1.0 | Auth & App State wiring | Wire AuthScreen to app state, restore sessions, and persist tokens with expo-secure-store. | Foundations | Critical | 12 | 2026-07-25 | 2026-07-27 | FALSE | Not Started |  | M1 | U-1..U-10 captured 2026-07-26. U-1: https://edu-platform-api-do20.onrender.com. U-7: Mac Day Aug 9. See docs/migration/m0-user-inputs.md
2.0 | Extend tokens with rarity + stage colors from web (claymorphic parity) | Port BRAND, RARITY_COLORS (common/rare/epic/legendary), STAGE_GRADIENTS + EVOLUTION_EMOJI (baby/child/teen/adult), CATEGORY_COLORS (home_family/nature/school_food/animals), CARE_STAT_COLORS, CLAY_TONE_SHADOWS, MOTION, CLAYMORPHIC_SPRINGS, and withOpacity into mobile/rn/src/design/tokens.ts. Reuse ClayCard/ClayButton/ClayProgressBar/ProgressTracker — no new visual primitives, no flat/glassmorphism/material defaults. Tokens mirror frontend-web/src/design-tokens/claymorphic.ts. | Foundations | Critical | 12 | 2026-07-27 | 2026-07-28 | FALSE | Not Started | 1.0 | M2 | Adds REQ-CLAY-001 enforcement. Reviewer §12 of the plan runs Rule-0 (no raw hex outside tokens.ts + clay primitives). Course and pet themes remain accessible.
3.0 | i18n Setup (en + vi) | Create English and Vietnamese catalogs and route every new user-visible string through i18n. | Foundations | Critical | 12 | 2026-07-28 | 2026-07-29 | FALSE | Not Started | 1.0 | M2 | No hardcoded screen copy
4.0 | Types + Service Layer (port course, lesson, pet, gamification types/services) | Port slim non-AR mobile types, authenticated services, hooks, environment-based API URL, and error handling. | Foundations | Critical | 28 | 2026-07-28 | 2026-07-31 | FALSE | Not Started | 1.0 | M3 | PHASE GATE: approve contracts before UI screens
5.0 | Course List Screen | Build responsive course catalog, progress states, loading, empty, error, and retry experiences using RN primitives. | Course Experience | Critical | 20 | 2026-08-03 | 2026-08-05 | FALSE | Not Started | 2.0,3.0,4.0 | M4 | Starts only after M3 sign-off
6.0 | Course Detail Screen | Show course metadata, ordered lessons, progress, and navigation into the lesson player. | Course Experience | Critical | 18 | 2026-08-05 | 2026-08-07 | FALSE | Not Started | 5.0 | M5 | Authenticated course detail flow
7.0 | Lesson Player Screen (without AR — flashcard-only or quiz-only) | Run non-AR lesson content, completion, and retry flows; AR references show an unavailable placeholder and never open Unity. | Course Experience | Critical | 24 | 2026-08-07 | 2026-08-11 | FALSE | Not Started | 6.0 | M5 | NO UnityView, bridge events, or AR session hooks
8.0 | Pet Hub Screen + components | Build PetsScreen, PetCard, PetGrid, PetSelector, and unlock/evolution modal with RN-native interaction patterns. | Pet Experience | Critical | 28 | 2026-08-06 | 2026-08-12 | FALSE | Not Started | 2.0,3.0,4.0 | M6 | Exclude 3D and AR pet viewers
9.0 | Gamification integration (XP bar, streak, pet unlocks) | Connect XP, streak, active pet, and unlock conditions; refresh state after relevant course and pet actions. | Integration | High | 20 | 2026-08-12 | 2026-08-14 | FALSE | Not Started | 7.0,8.0 | M7 | Contract-derived user identity only
10.0 | Navigation refactor (bottom tabs: Home / Courses / Pets / Profile placeholder) | Add authenticated bottom tabs, preserve existing routes, and keep the Profile tab as a localized placeholder. | Integration | Critical | 16 | 2026-08-14 | 2026-08-17 | FALSE | Not Started | 5.0,8.0,9.0 | M7 | PHASE GATE: feature-complete review
11.0 | Polish + iOS smoke test | Run type checks, reviewer pass, manual iOS-only smoke checklist, accessibility checks, and release-readiness sign-off. | Polish & Test | Critical | 24 | 2026-08-18 | 2026-08-20 | FALSE | Not Started | 10.0 | M9 | NO Android validation; no Unity or AR core changes

## Daily Checklist
Day | Date | Weekday | Phase / Focus | Daily Deliverables | WBS | Done | % Complete | Blockers | Milestone / Gate | Exit Notes
1 | 2026-07-25 | Saturday | Setup & Plan | Lock scope, inspect reference tracker, baseline contracts, and confirm NO Unity/AR core and iOS-only constraints. | 1.0 | TRUE | 10000% | U-1..U-10 captured; U-9/U-10 deferred | M0 | M0 captured 2026-07-26. U-1: https://edu-platform-api-do20.onrender.com ¦ U-2: no API key (open) ¦ U-7: Mac Day Aug 9 ¦ U-6: iOS 26.5 (beta). See docs/migration/m0-user-inputs.md. U-9 (Edge Functions) deferred: plan uses FastAPI only.
2 | 2026-07-27 | Monday | Auth & App State | Wire login/logout/session restoration and verify secure token lifecycle. | 1.0,2.0 | FALSE | 0% |  | M1 | M1 sign-off.
3 | 2026-07-28 | Tuesday | Design + i18n | Extend course/pet clay tokens and scaffold en/vi catalogs. | 2.0,3.0,4.0 | FALSE | 0% |  | M2 | Review contrast and key naming.
4 | 2026-07-29 | Wednesday | Design + i18n | Complete bilingual foundation and approve reusable visual patterns. Run Reviewer §12 Rule-0 grep and claymorphic compliance checks on the new tokens. | 3.0,4.0 | FALSE | 0% |  | M2 | M2 sign-off. Designer + Reviewer sign-off on RARITY_COLORS / STAGE_GRADIENTS / CATEGORY_COLORS parity vs web.
5 | 2026-07-30 | Thursday | Service Foundation | Port slim course, lesson, pet, and gamification contracts and services. | 4.0 | FALSE | 0% |  | M3 | Use EXPO_PUBLIC_API_URL.
6 | 2026-07-31 | Friday | Foundation Gate | Finish backend audit, type checks, hooks, error handling, and M3 review. | 4.0 | FALSE | 0% |  | M3 | STOP: no screens before sign-off.
7 | 2026-08-03 | Monday | Course Catalog | Build course list loading, success, empty, error, and retry states. | 5.0 | FALSE | 0% |  | M4 | Use FlatList and stable keys.
8 | 2026-08-04 | Tuesday | Course Catalog | Add grouping, progress, localized metadata, and navigation behavior. | 5.0 | FALSE | 0% |  | M4 | Screen review.
9 | 2026-08-05 | Wednesday | Course Catalog | Complete course list acceptance and begin detail shell. | 5.0,6.0 | FALSE | 0% |  | M4 | M4 sign-off.
10 | 2026-08-06 | Thursday | Course + Pets | Build course detail and start pet grid/components in parallel. | 6.0,8.0 | FALSE | 0% |  | M5 | No 3D/AR pet viewers.
11 | 2026-08-07 | Friday | Course Detail | Complete lesson ordering, progress, and player navigation. | 6.0,7.0 | FALSE | 0% |  | M5 | Authenticated route test.
12 | 2026-08-10 | Monday | Lesson Player | Build flashcard/quiz flow, completion call, and AR-reference placeholder. | 7.0,8.0 | FALSE | 0% |  | M5 | Never invoke Unity.
13 | 2026-08-11 | Tuesday | Lesson Player | Finish error/retry/completion states and course learning flow review. | 7.0,8.0 | FALSE | 0% |  | M5 | M5 sign-off.
14 | 2026-08-12 | Wednesday | Pet Hub | Complete active pet, care actions, selector, and unlock/evolution feedback. | 8.0,9.0 | FALSE | 0% |  | M6 | M6 sign-off.
15 | 2026-08-13 | Thursday | Gamification | Integrate XP, level, streak, and unlock eligibility state. | 9.0 | FALSE | 0% |  | M7 | Refresh after mutations.
16 | 2026-08-14 | Friday | Integration | Finish gamification integration and build bottom tab navigation. | 9.0,10.0 | FALSE | 0% |  | M7 | Preserve existing routes.
17 | 2026-08-17 | Monday | Integration Gate | Review tabs, localization, API behavior, scope, and feature acceptance. Run the full Reviewer §12 claymorphic checklist (static + visual) on every new screen under mobile/rn/src/screens and mobile/rn/src/components/pets. | 10.0 | FALSE | 0% |  | M7 | STOP: no polish before sign-off. No Critical REQ-CLAY-001 issues remain open.
18 | 2026-08-18 | Tuesday | Polish | Resolve review findings, accessibility issues, type errors, and visual inconsistencies. | 11.0 | FALSE | 0% |  | M8 | iOS-only readiness.
19 | 2026-08-19 | Wednesday | iOS Smoke | Run available iOS environment smoke checklist and record evidence/blockers. | 11.0 | FALSE | 0% |  | M8 | Do not substitute Android.
20 | 2026-08-20 | Thursday | Release Readiness | Close critical requirements and risks; complete M9 sign-off and handoff. | 11.0 | FALSE | 0% |  | M9 | Unity/AR core diff must remain empty.

## Risk Register
Risk_ID | Risk_Description | Category | Probability | Impact | Risk_Score | Mitigation_Strategy | Contingency_Plan | Owner | Status | Notes
R-001 | Backend route or response shapes differ from the web service assumptions. | Technical | High | Critical | Critical | Complete contract audit by M3; use typed adapters and fixtures. | Block UI work and resolve contract at service boundary. | Frontend + Backend | Open | Foundation gate blocker
R-002 | Stored token restoration or expiry handling causes an authentication loop. | Technical | Medium | Critical | High | Test valid, missing, expired, and revoked token paths in WBS 1.0. | Clear secure token and return to AuthScreen. | Frontend | Open | M1 gate
R-003 | Pet assets or backend pet states are incomplete. | Data | Medium | High | Medium | Audit pet payload and provide deterministic image/state fallback rules. | Use localized placeholder art and disable unsupported action. | Frontend + Backend | Open | No 3D fallback
R-004 | AR fields leak into the lesson player and create a Unity dependency. | Scope | Medium | Critical | High | Slim mobile types; enforce placeholder behavior; inspect imports at review gates. | Remove coupling and revert any Unity/AR file change. | Reviewer | Open | Hard scope constraint
R-005 | i18n coverage is incomplete or Vietnamese copy overflows layouts. | Quality | Medium | High | Medium | Catalog-first strings and bilingual screen review by M7. | Block sign-off until missing keys and overflow are fixed. | Frontend | Open | All new copy localized
R-006 | Course or pet lists perform poorly on older iPhones. | Performance | Medium | High | Medium | Use FlatList, stable keys, memoized rows, and image sizing. | Reduce simultaneous rendering and defer non-critical content. | Frontend | Open | iOS-only performance
R-007 | Navigation refactor breaks existing Auth, Home, or dormant routes. | Technical | Medium | Critical | High | Preserve route names and smoke every existing route at M7. | Revert tab shell and restore previous navigator mapping. | Frontend | Open | No file deletion
R-008 | Gamification state becomes stale after lesson or pet mutations. | Technical | Medium | High | Medium | Centralize refresh/invalidation after successful mutations. | Force summary refetch and show non-blocking retry. | Frontend | Open | WBS 9.0
R-009 | Windows development environment cannot execute an iOS simulator smoke test. | Environment | High | High | High | Prepare an explicit iOS checklist and reserve an available Mac/iPhone for M8. | Record blocker; complete static/type checks and defer device-only evidence. | Project Manager | Open | Do not substitute Android
R-010 | Expo SDK or React Navigation package compatibility blocks the tab navigator. | Dependency | Medium | High | Medium | Use Expo-compatible package versions and validate before WBS 10.0. | Use stack navigation temporarily while resolving compatible tabs. | Frontend | Open | No speculative upgrades
R-011 | The API is unavailable during implementation or smoke testing. | External | Medium | High | Medium | Keep typed fixtures for UI states and schedule integration checks at M3/M7. | Continue fixture-based work; do not claim integrated acceptance. | Backend | Open | Integration evidence required
R-012 | Scope creep adds profile, admin, marketing, Android, 3D, or AR work. | Schedule | Medium | Critical | High | Use WBS and requirement scope at every gate; reject unplanned additions. | Defer additions to a separate backlog and protect critical path. | Project Manager | Open | 20-day budget
R-013 | Course content fields are too broad for the slim mobile type model. | Technical | Medium | Medium | Medium | Map only fields consumed by mobile and document ignored optional fields. | Extend the adapter with optional typed fields after contract review. | Frontend | Open | Avoid copying massive web type
R-014 | Critical work overruns the 20-working-day schedule. | Schedule | Medium | Critical | High | Daily checklist, predecessor tracking, and immediate escalation at phase gates. | Cut Should/Could polish while retaining all Must requirements. | Project Manager | Open | M9 fixed target
R-015 | Accessibility issues are found late in polish. | Quality | Medium | High | Medium | Apply labels, touch targets, contrast, and dynamic text during each screen task. | Fix critical accessibility failures before M8. | Frontend + Reviewer | Open | iOS review

## Gantt Chart
Courses + Pets RN Migration — 20-Working-Day Gantt
Timeline: 2026-07-25 to 2026-08-20 ¦ iOS only ¦ NO Unity/AR core ¦ Gates: M3, M7, M8
Task / Gate | Milestone | 2026-07-25 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | Gate / Acceptance Notes
WBS / Gate | ID | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | Evidence required before proceeding
1.0 Auth & App State wiring | M1 | bar: 2026-07-25 to 2026-08-20
2.0 Extend tokens with rarity + stage colors from web (claymorphic parity) | M2 | [20 empty] | REQ-CLAY-001 enforced. RARITY_COLORS / STAGE_GRADIENTS / EVOLUTION_EMOJI / CATEGORY_COLORS / CARE_STAT_COLORS / CLAY_TONE_SHADOWS / MOTION / CLAYMORPHIC_SPRINGS / withOpacity added to mobile/rn/src/design/tokens.ts. | bar: 2026-07-27 to 2026-07-28
3.0 i18n Setup (en + vi) | M2 | bar: 2026-07-25 to 2026-08-20
4.0 Types + Service Layer (port course, lesson, pet, gamification types/services) | M3 | bar: 2026-07-28 to 2026-07-31
5.0 Course List Screen | M4 | bar: 2026-07-25 to 2026-08-20
6.0 Course Detail Screen | M5 | bar: 2026-08-05 to 2026-08-07
7.0 Lesson Player Screen (without AR — flashcard-only or quiz-only) | M5 | bar: 2026-07-25 to 2026-08-20
8.0 Pet Hub Screen + components | M6 | bar: 2026-08-06 to 2026-08-12
9.0 Gamification integration (XP bar, streak, pet unlocks) | M7 | bar: 2026-07-25 to 2026-08-20
10.0 Navigation refactor (bottom tabs: Home / Courses / Pets / Profile placeholder) | M7 | bar: 2026-08-14 to 2026-08-17
11.0 Polish + iOS smoke test | M9 | bar: 2026-07-25 to 2026-08-20
PHASE GATES / MILESTONES
◆ Scope & Baseline Locked | M0 | [20 empty] | Scope confirms courses + pets only; Unity/AR core and Android excluded. | bar: 2026-07-25
◆ Auth & App State Ready | M1 | [20 empty] | Gate: authenticated app shell restores and clears sessions safely. | bar: 2026-07-25 to 2026-08-20
◆ Design System & i18n Ready | M2 | [20 empty] | Gate: reusable clay tokens and en/vi catalogs approved. | bar: 2026-07-29
◆ Foundation Phase Gate | M3 | [20 empty] | Mandatory sign-off on API contracts, types, services, hooks, and backend audit before screens. | bar: 2026-07-25 to 2026-08-20
◆ Course Catalog Ready | M4 | [20 empty] | Course list acceptance criteria pass. | bar: 2026-08-05
◆ Course Learning Flow Ready | M5 | [20 empty] | Course detail and non-AR lesson player pass; AR references degrade safely. | bar: 2026-07-25 to 2026-08-20
◆ Pet Hub Ready | M6 | [20 empty] | Pet catalog, active selection, care actions, and unlock UI pass. | bar: 2026-08-12
◆ Feature Integration Gate | M7 | [20 empty] | Mandatory reviewer sign-off for gamification, tabs, localization, and scope compliance. | bar: 2026-07-25 to 2026-08-20
◆ iOS Smoke Gate | M8 | [20 empty] | iOS-only configuration and manual smoke checklist pass in an available iOS environment. | bar: 2026-08-19
◆ Migration Release Ready | M9 | [20 empty] | Final acceptance, documentation, and handoff complete; Unity/AR core remains untouched. | bar: 2026-07-25 to 2026-08-20