## Dashboard
AR Engine Build Tracker — Dashboard
Metric | Value | Target / Meaning | Notes
Total tasks | 37 | Dynamic | Calculated from tracker sheets
Tasks done | 0 | Dynamic | Calculated from tracker sheets
Tasks remaining | 42 | Dynamic | Calculated from tracker sheets
% complete | 0% | Dynamic | Calculated from tracker sheets
Total requirements | 34 | Dynamic | Calculated from tracker sheets
Critical requirements | 19 | Dynamic | Calculated from tracker sheets
Critical risks | 1 | Dynamic | Calculated from tracker sheets
Mac Day countdown | 13 | Dynamic | Calculated from tracker sheets

## Project Info
Project Metadata | Value
Project Name | AR Food Education App - Engine Build
Project ID | AR-EDU-2026-001
Start Date | 2026-07-25
Target Completion | 2026-08-19
Total Working Days | 20
Mac Day | 2026-08-07 (Day 13)
Project Manager | Me
Status | Active
Demo Date | 2026-08-19
Demo Type | Local iOS only
Stack | React Native + Unity 6.0 + ARFoundation 6.3.5

## Milestones
Milestone_ID | Milestone_Name | Target_Date | Done | %_Complete | Status | Dependencies | Risk_Level | Sign_Off | Notes
M0 | Foundation Audit | 2026-07-25 | FALSE | 0 | Not Started | None | Green | FALSE | Day 1 gate
M1 | Foundation Complete | 2026-07-27 | FALSE | 0 | Not Started | M0 | Green | FALSE | Day 2 gate
M2 | Unity AR Working | 2026-07-29 | FALSE | 0 | Not Started | M1 | Green | FALSE | Day 4 gate
M3 | Bridge Functional | 2026-07-31 | FALSE | 0 | Not Started | M2 | Green | FALSE | Day 6 gate
M4 | API Integrated | 2026-08-03 | FALSE | 0 | Not Started | M3 | Green | FALSE | Day 8 gate
M5 | UI Complete | 2026-08-05 | FALSE | 0 | Not Started | M4 | Green | FALSE | Day 10 gate
M6 | Code Freeze | 2026-08-09 | FALSE | 0 | Not Started | M5 | Green | FALSE | Day 12 gate
M7 | Demo Ready | 2026-08-19 | FALSE | 0 | Not Started | M6 | Green | FALSE | Day 20 final

## Requirements
Req_ID | Category | Requirement_Description | Priority | MoSCoW | Status | Done | Verification_Method | Notes
REQ-001 | Functional | RN App shall launch to a Home screen with 3 lesson cards | Critical | Must | Not Started | FALSE | Manual test on iOS
REQ-002 | Functional | App shall scan for AR image targets using ARKit | Critical | Must | Not Started | FALSE | Scan elephant printout
REQ-003 | Functional | On image detection, Unity shall spawn 3D elephant model | Critical | Must | Not Started | FALSE | Visual confirmation
REQ-004 | Functional | On detection, jungle scene shall appear around elephant | Critical | Must | Not Started | FALSE | Visual confirmation
REQ-005 | Functional | User shall see word + translation overlay in RN | Critical | Must | Not Started | FALSE | Visual confirmation
REQ-006 | Functional | RN ↔ Unity bridge shall pass messages both directions | Critical | Must | Not Started | FALSE | Test bridge
REQ-007 | Functional | App shall fetch food data from web API | Critical | Must | Not Started | FALSE | curl API endpoint
REQ-013 | Non-Functional | App shall not crash during 5-min demo | Critical | Must | Not Started | FALSE | 5-min stress test
REQ-014 | Non-Functional | Code shall compile without errors on Mac Day | Critical | Must | Not Started | FALSE | Xcode build success
REQ-015 | Non-Functional | iOS .ipa shall install via Xcode | Critical | Must | Not Started | FALSE | Xcode install
REQ-016 | Technical | Use Unity 6.0 (6000.3.20f1) | Critical | Must | Not Started | FALSE | Check Editor version
REQ-017 | Technical | Use ARFoundation 6.3.5 | Critical | Must | Not Started | FALSE | Check manifest.json
REQ-019 | Technical | GLBLoader.cs shall exist and parse .glb files | Critical | Must | Not Started | FALSE | Unity Console clean | MISSING - must create
REQ-020 | Technical | ModelSpawner.cs shall instantiate prefabs on image track | Critical | Must | Not Started | FALSE | Elephant spawns | MISSING - must create
REQ-021 | Technical | AnimationController.cs shall play walk/idle anims | Critical | Must | Not Started | FALSE | Anim plays | MISSING - must create
REQ-022 | Technical | iOS Swift bridge shall connect RN to Unity | Critical | Must | Not Started | FALSE | Bridge test | MISSING - must create
REQ-029 | Demo | Demo video (3 min) shall be recorded as backup | Critical | Must | Not Started | FALSE | Video file exists
REQ-030 | Demo | Slides (5-7) shall explain architecture | Critical | Must | Not Started | FALSE | Slides file
REQ-033 | Demo | Printed elephant image shall be on hand | Critical | Must | Not Started | FALSE | Print
REQ-008 | Functional | On elephant tap, nutrition info shall display | High | Should | Not Started | FALSE | Tap to show data
REQ-010 | Functional | App shall handle no-internet state gracefully | High | Should | Not Started | FALSE | Turn off WiFi test
REQ-012 | Non-Functional | AR tracking shall lock onto image within 2 seconds | High | Should | Not Started | FALSE | Timer from detect to spawn
REQ-018 | Technical | Use React Native 0.73+ | High | Should | Not Started | FALSE | Check package.json
REQ-023 | Technical | API service shall use fetch with error handling | High | Should | Not Started | FALSE | API call works
REQ-024 | UX | Home screen shall display lesson cards in grid | High | Should | Not Started | FALSE | Visual
REQ-027 | UX | AR camera shall have close button to exit | High | Should | Not Started | FALSE | Tap close
REQ-031 | Demo | Demo script shall be rehearsed (3x) | High | Should | Not Started | FALSE | Practice run
REQ-032 | Demo | Backup iPhone shall be charged and ready | High | Should | Not Started | FALSE | Charge + test
REQ-009 | Functional | Audio shall play when elephant spawns | Medium | Should | Not Started | FALSE | Listen for audio
REQ-011 | Non-Functional | App shall load Home screen in < 3 seconds | Medium | Should | Not Started | FALSE | Timer test
REQ-025 | UX | Loading state shall show spinner during fetch | Medium | Should | Not Started | FALSE | Visual
REQ-026 | UX | Error state shall show retry button | Medium | Should | Not Started | FALSE | Visual
REQ-034 | Demo | README shall explain how to run the app | Medium | Should | Not Started | FALSE | README exists
REQ-028 | UX | Nutrition info shall animate in (fade) | Low | Could | Not Started | FALSE | Visual

## WBS Checklist
WBS_ID | Task_Name | Description | Priority | Effort_Hours | Start_Date | End_Date | Predecessors | Done | Status | Blockers | Milestone | Notes
1.1 | Verify Unity 6.0 installed | Check Unity Hub for 6000.3.20f1 | Critical | 0.5 | 2026-07-25 | 2026-07-25 |  | FALSE | Not Started |  | M0
1.2 | Run npm install in mobile/ | Install RN deps | Critical | 1 | 2026-07-25 | 2026-07-25 |  | FALSE | Not Started |  | M0
1.3 | Capture user inputs U-1 to U-10 | Get API URL and key info | Critical | 1 | 2026-07-25 | 2026-07-25 |  | FALSE | Not Started |  | M0
2.1 | Verify ARFoundation 6.3.5 | Check manifest.json | Critical | 0.25 | 2026-07-27 | 2026-07-27 | 1.0 | FALSE | Not Started |  | M1
2.2 | Verify RuntimeImageTrackingPOC.cs | Check AF6 API usage | Critical | 0.5 | 2026-07-27 | 2026-07-27 | 2.1 | FALSE | Not Started |  | M1
2.3 | Verify ARSessionManager.cs | Check AF6 API usage | Critical | 0.5 | 2026-07-27 | 2026-07-27 | 2.1 | FALSE | Not Started |  | M1
2.4 | Verify AnchorManager.cs | Check AF6 API usage | Critical | 0.5 | 2026-07-27 | 2026-07-27 | 2.1 | FALSE | Not Started |  | M1
2.5 | Verify PlaneDetection.cs | Check AF6 API usage | Critical | 0.5 | 2026-07-27 | 2026-07-27 | 2.1 | FALSE | Not Started |  | M1
2.7 | Create GLBLoader.cs | NEW - parse .glb files | Critical | 3 | 2026-07-28 | 2026-07-28 | 2.1 | FALSE | Not Started |  | M1 | MISSING
2.8 | Create ModelSpawner.cs | NEW - instantiate prefabs | Critical | 2 | 2026-07-28 | 2026-07-28 | 2.7 | FALSE | Not Started |  | M1 | MISSING
2.9 | Create AnimationController.cs | NEW - play animations | Critical | 2 | 2026-07-28 | 2026-07-28 | 2.8 | FALSE | Not Started |  | M1 | MISSING
2.10 | Test AR on iPhone | Print elephant scan | Critical | 3 | 2026-07-29 | 2026-07-29 | 2.9 | FALSE | Not Started |  | M2
3.1 | Update RNMessageReceiver.cs | Unity 6.x API | Critical | 1 | 2026-07-30 | 2026-07-30 | 2.0 | FALSE | Not Started |  | M3
3.2 | Update RNEventEmitter.cs | Unity 6.x API | Critical | 1 | 2026-07-30 | 2026-07-30 | 2.0 | FALSE | Not Started |  | M3
3.3 | Create iOS Swift bridge | RNMessageReceiverBridge.swift | Critical | 3 | 2026-07-30 | 2026-07-30 | 3.1 | FALSE | Not Started |  | M3 | MISSING
3.4 | Test RN→Unity send message | One-way bridge test | Critical | 2 | 2026-07-31 | 2026-07-31 | 3.3 | FALSE | Not Started |  | M3
3.5 | Test Unity→RN send message | Other-way bridge test | Critical | 2 | 2026-07-31 | 2026-07-31 | 3.4 | FALSE | Not Started |  | M3
4.1 | Get API base URL from user | Confirm endpoint | Critical | 0.5 | 2026-08-01 | 2026-08-01 |  | FALSE | Not Started |  | M4 | API URL needed
4.2 | Test API with curl | Verify endpoint works | Critical | 0.5 | 2026-08-01 | 2026-08-01 | 4.1 | FALSE | Not Started |  | M4
4.3 | Create api.ts service | RN fetch wrapper | Critical | 2 | 2026-08-01 | 2026-08-01 | 4.1 | FALSE | Not Started |  | M4
4.4 | Wire Home screen to API | Fetch and display | Critical | 3 | 2026-08-02 | 2026-08-02 | 4.3 | FALSE | Not Started |  | M4
6.2 | Mac Day - Unity iOS build | Generate Xcode project | Critical | 3 | 2026-08-07 | 2026-08-07 | 6.1 | FALSE | Not Started | Mac required | M6
6.3 | Mac Day - Xcode build | Compile to .ipa | Critical | 2 | 2026-08-07 | 2026-08-07 | 6.2 | FALSE | Not Started | Mac required | M6
6.4 | Install on iPhone | Xcode local install | Critical | 1 | 2026-08-07 | 2026-08-07 | 6.3 | FALSE | Not Started |  | M6
6.5 | Smoke test on device | Run app scan test | Critical | 1 | 2026-08-07 | 2026-08-07 | 6.4 | FALSE | Not Started |  | M6
7.1 | Bug fixes from on-device test | Fix top 5 bugs | Critical | 4 | 2026-08-08 | 2026-08-08 | 6.5 | FALSE | Not Started |  | M7
7.6 | Print elephant image | Test target | Critical | 1 | 2026-08-18 | 2026-08-18 |  | FALSE | Not Started |  | M7
7.7 | Final defense | Present to committee | Critical | 2 | 2026-08-19 | 2026-08-19 | 7.5 | FALSE | Not Started |  | M7
1.4 | Confirm Mac Day booked | Schedule 1 Mac day | High | 0.5 | 2026-07-25 | 2026-07-25 |  | FALSE | Not Started |  | M0
2.6 | Verify ARGestureHandler.cs | Check gesture handling | High | 1 | 2026-07-27 | 2026-07-27 | 2.1 | FALSE | Not Started |  | M1
4.5 | Add loading state | Spinner component | High | 1 | 2026-08-02 | 2026-08-02 | 4.4 | FALSE | Not Started |  | M4
4.6 | Add error state | Retry button | High | 1 | 2026-08-03 | 2026-08-03 | 4.5 | FALSE | Not Started |  | M4
5.1 | Home screen layout | Grid of cards | High | 2 | 2026-08-04 | 2026-08-04 | 4.4 | FALSE | Not Started |  | M5
5.2 | AR camera screen | Unity container | High | 3 | 2026-08-04 | 2026-08-04 | 5.1 | FALSE | Not Started |  | M5
5.3 | Food details screen | Nutrition display | High | 2 | 2026-08-05 | 2026-08-05 | 5.2 | FALSE | Not Started |  | M5
5.4 | Add navigation | React Navigation | High | 2 | 2026-08-05 | 2026-08-05 | 5.3 | FALSE | Not Started |  | M5
6.1 | Pre-Mac prep | Sync code to repo | High | 1 | 2026-08-06 | 2026-08-06 | 5.0 | FALSE | Not Started |  | M6
7.2 | Record demo video (3 min) | Backup video | High | 2 | 2026-08-10 | 2026-08-10 | 7.1 | FALSE | Not Started |  | M7
7.4 | Create slides (5-7) | Architecture + demo | High | 3 | 2026-08-15 | 2026-08-15 | 7.2 | FALSE | Not Started |  | M7
7.5 | Rehearse demo (3x) | Practice run | High | 2 | 2026-08-18 | 2026-08-18 | 7.4 | FALSE | Not Started |  | M7
5.5 | Style polish | Basic CSS | Medium | 1 | 2026-08-05 | 2026-08-05 | 5.4 | FALSE | Not Started |  | M5
7.3 | Write README | How to run | Medium | 2 | 2026-08-12 | 2026-08-12 | 7.1 | FALSE | Not Started |  | M7

## Daily Checklist
Day | Date | Day_Name | Focus_Area | Tasks_Today | Done | Hours_Logged | Blockers | EOD_Status | Milestone
1 | 2026-07-25 | Saturday | Foundation | Verify Unity; npm install; capture inputs; book Mac Day; print elephant | FALSE | 0 |  |  | M0
2 | 2026-07-27 | Monday | Unity Foundation | Verify manifest.json; verify 5 C# scripts | FALSE | 0 |  |  | M1
3 | 2026-07-28 | Tuesday | Unity Scripts | Create GLBLoader; create ModelSpawner; create AnimationController | FALSE | 0 |  |  | M1
4 | 2026-07-29 | Wednesday | AR Test | Open Unity; check Console; test AR on iPhone with elephant printout | FALSE | 0 |  |  | M2
5 | 2026-07-30 | Thursday | Bridge | Update RNMessageReceiver; update RNEventEmitter; create iOS Swift bridge | FALSE | 0 |  |  | M3
6 | 2026-07-31 | Friday | Bridge Test | Test RN→Unity; test Unity→RN; verify 2-way bridge | FALSE | 0 |  |  | M3
7 | 2026-08-01 | Saturday | API Setup | Get API URL; test with curl; create api.ts; wire Home screen | FALSE | 0 |  |  | M4
8 | 2026-08-02 | Sunday | API Integration | Add loading state; add error state; verify data flows | FALSE | 0 |  |  | M4
9 | 2026-08-03 | Monday | UI Screens | Home screen; AR camera screen; Food details screen | FALSE | 0 |  |  | M5
10 | 2026-08-04 | Tuesday | UI Polish | Add React Navigation; style polish; verify 3 screens | FALSE | 0 |  |  | M5
11 | 2026-08-05 | Wednesday | Code Freeze | Final code review; commit to git; tag v1.0 | FALSE | 0 |  |  | M6
12 | 2026-08-06 | Thursday | Pre-Mac Prep | Sync code; verify Mac access; pre-build check | FALSE | 0 |  |  | M6
13 | 2026-08-07 | Friday | Mac Day | Unity iOS build; Xcode compile; install on iPhone; smoke test | FALSE | 0 | Mac required |  | M6
14 | 2026-08-08 | Saturday | Bug Fixes | Test on real device; fix top 5 bugs; re-test | FALSE | 0 |  |  | M7
15 | 2026-08-10 | Monday | Demo Video | Record 3-min demo video; save as backup | FALSE | 0 |  |  | M7
16 | 2026-08-12 | Wednesday | README | Write README; architecture doc; setup instructions | FALSE | 0 |  |  | M7
17 | 2026-08-15 | Saturday | Slides | Create 5-7 slides; architecture diagram; demo flow | FALSE | 0 |  |  | M7
18 | 2026-08-18 | Tuesday | Rehearsal | Practice demo 3x; print elephant; charge spare phone | FALSE | 0 |  |  | M7
19 | 2026-08-19 | Wednesday | Final Prep | Charge all devices; backup iPhone ready; video ready | FALSE | 0 |  |  | M7
20 | 2026-08-19 | Wednesday | Defense | Present to committee; demo live; answer questions | FALSE | 0 |  |  | M7

## Risk Register
Risk_ID | Risk_Description | Category | Probability | Impact | Risk_Score | Mitigation_Strategy | Contingency_Plan | Owner | Status | Notes
R-016 | Missing C# scripts not discovered | Technical | High | Critical | Critical | Inventory repo Day 1; create GLBLoader/ModelSpawner/AnimationController Day 3 | Use placeholder scripts | Me | Open | Known gap
R-014 | Time overrun on critical path | Schedule | High | High | High | Daily standups; early escalation | Cut scope to 1 model only | Me | Open | Most likely risk
R-017 | Bugs found late in Mac Day | Technical | High | High | High | Pre-Mac prep on Day 12 | Patch and ship anyway | Me | Open
R-002 | Mac not available for build | Schedule | Medium | Critical | High | Book Mac Day now; have backup Mac identified | Skip iOS build use Android | Me | Open | Critical gate
R-003 | API URL not provided | External | Medium | Critical | High | Ask user for U-1 on Day 1 | Use mock data with hardcoded responses | Me | Open | Blocker for Day 7
R-008 | iOS code signing fails | Technical | Medium | Critical | High | Set up Apple ID Day 1; verify certs | Use development cert workaround | Me | Open | Mac Day critical
R-011 | Unity-RN bridge doesn't communicate | Technical | Medium | Critical | High | Test bridge Day 6 with simple message | Use deep linking as fallback | Me | Open | Critical for demo
R-012 | iOS .ipa install fails on device | Technical | Medium | Critical | High | Test install Day 7 immediately | Use simulator for demo | Me | Open
R-013 | App crashes during demo | Technical | Medium | Critical | High | Stress test Day 14; record backup video | Show video instead of live demo | Me | Open | Critical
R-018 | Build environment misconfigured | Technical | Medium | Critical | High | Test build Day 3 to fail fast | Rebuild from scratch | Me | Open
R-001 | Unity 6000.3.20f1 not installed | Technical | Low | Critical | Medium | Install via Unity Hub early on Day 1 | Use alternative version | Me | Open | Low risk - quick fix
R-004 | API endpoint changes during sprint | External | Low | High | Medium | Lock API spec before Day 7 | Use cached response data | Me | Open
R-005 | Elephant .glb model incompatible | Technical | Low | High | Medium | Test import in Unity Day 1 | Use cube primitive as fallback | Me | Open | Quick check Day 1
R-006 | Jungle scene missing or broken | Technical | Low | High | Medium | Verify scene exists Day 1 | Use simple plane background | Me | Open
R-007 | ARFoundation 6.3.5 package not resolving | Technical | Low | Critical | Medium | Verify manifest.json Day 2 | Downgrade to 6.3.4 | Me | Open
R-009 | iPhone device not available | Resource | Low | Critical | Medium | Confirm iPhone + iOS version Day 1 | Borrow friend's iPhone | Me | Open | Required for testing
R-010 | ARKit not supported on test device | Technical | Low | Critical | Medium | Check device compatibility Day 1 | Use Android with ARCore instead | Me | Open | Need A12+ chip
R-015 | Scope creep mid-sprint | Schedule | Medium | Medium | Medium | Lock scope at M6 code freeze | Reject new features | Me | Open
R-019 | Egypt timezone conflict for support | External | Low | Low | Low | Plan ahead; batch questions | Proceed with defaults | Me | Open
R-020 | Printer not available for elephant image | Resource | Low | Medium | Low | Confirm printer Day 1 | Print at copy shop | Me | Open | Required Day 18

## Gantt Chart
AR Engine Build Tracker — Gantt Timeline
Timeline: 2026-07-25 to 2026-08-19 ¦ Mac Day: 2026-08-07
Task | Milestone | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19
Task | Milestone | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
1.1 Verify Unity 6.0 installed | M0 | bar: 2026-07-25
1.2 Run npm install in mobile/ | M0 | bar: 2026-07-25
1.3 Capture user inputs U-1 to U-10 | M0 | bar: 2026-07-25
2.1 Verify ARFoundation 6.3.5 | M1 | bar: 2026-07-27
2.2 Verify RuntimeImageTrackingPOC.cs | M1 | bar: 2026-07-27
2.3 Verify ARSessionManager.cs | M1 | bar: 2026-07-27
2.4 Verify AnchorManager.cs | M1 | bar: 2026-07-27
2.5 Verify PlaneDetection.cs | M1 | bar: 2026-07-27
2.7 Create GLBLoader.cs | M1 | bar: 2026-07-28
2.8 Create ModelSpawner.cs | M1 | bar: 2026-07-28
2.9 Create AnimationController.cs | M1 | bar: 2026-07-28
2.10 Test AR on iPhone | M2 | bar: 2026-07-29
3.1 Update RNMessageReceiver.cs | M3 | bar: 2026-07-30
3.2 Update RNEventEmitter.cs | M3 | bar: 2026-07-30
3.3 Create iOS Swift bridge | M3 | bar: 2026-07-30
3.4 Test RN→Unity send message | M3 | bar: 2026-07-31
3.5 Test Unity→RN send message | M3 | bar: 2026-07-31
4.1 Get API base URL from user | M4 | bar: 2026-08-01
4.2 Test API with curl | M4 | bar: 2026-08-01
4.3 Create api.ts service | M4 | bar: 2026-08-01
4.4 Wire Home screen to API | M4 | bar: 2026-08-02
6.2 Mac Day - Unity iOS build | M6 | bar: 2026-08-07
6.3 Mac Day - Xcode build | M6 | bar: 2026-08-07
6.4 Install on iPhone | M6 | bar: 2026-08-07
6.5 Smoke test on device | M6 | bar: 2026-08-07
7.1 Bug fixes from on-device test | M7 | bar: 2026-08-08
7.6 Print elephant image | M7 | bar: 2026-08-18
7.7 Final defense | M7 | bar: 2026-08-19
1.4 Confirm Mac Day booked | M0 | bar: 2026-07-25
2.6 Verify ARGestureHandler.cs | M1 | bar: 2026-07-27
4.5 Add loading state | M4 | bar: 2026-08-02
4.6 Add error state | M4 | bar: 2026-08-03
5.1 Home screen layout | M5 | bar: 2026-08-04
5.2 AR camera screen | M5 | bar: 2026-08-04
5.3 Food details screen | M5 | bar: 2026-08-05
5.4 Add navigation | M5 | bar: 2026-08-05
6.1 Pre-Mac prep | M6 | bar: 2026-08-06
7.2 Record demo video (3 min) | M7 | bar: 2026-08-10
7.4 Create slides (5-7) | M7 | bar: 2026-08-15
Legend | M0 — Foundation Audit | 2026-07-25: M1 — Foundation Complete; 2026-07-26: M2 — Unity AR Working; 2026-07-27: M3 — Bridge Functional; 2026-07-28: M4 — API Integrated; 2026-07-29: M5 — UI Complete; 2026-07-30: M6 — Code Freeze; 2026-07-31: M7 — Demo Ready; 2026-08-18: ✓
5.5 Style polish | M5 | bar: 2026-08-05
7.3 Write README | M7 | bar: 2026-08-12